## Material Requisition & Delivery
TO BE UPDATED BY |  |  | PROJECT TEAM | [5 empty] | PROCUREMENT | PROJECT MANAGER | ERP PROCUREMENT PROCESS |  |  |  | PROCUREMENT |  | SITE STORE Incharge
Indent No | Indent Date | BOQ NO | DESCRIPTION OF MATERIAL REQUIRED | Size & Specification | Qty | Unit | Mention the Date - Material Required at Site | Remark | Clarification Required (if Any) | Comments from Project Manager - Site Instruction Details or Any other reference For NT Items | STORE REQUISITION NUMBER & DATE | QTY OF MATERIAL AVAILABLE AT WAREHOUSE/STORE | QTY OF MATERIAL TO BE PROCURED | PURCHASE REQUISITION NUMBER & DATE | PURCHASE ORDER NUMBER & DATE | QUANTITY | DATE OF RECIEPT OF MATERIAL AT SITE | RECIEVED QUANTITY | ISSUED QUANTITY | BALANCE QTY | REMARKS (If Any)
STR-01 | 23/08/2019 | NA | Printing Of Delivery Challan Books |  | 10 | Num | 26/08/2019 | Returnable |  | Still materials not received | 00263 & 26/8/19 |  |  | 00145 & 26-Aug-2019 | 00055-CHN/19-20 / 27-Aug-2019 | 10 | 2019-04-09 | 2 | 2 | 0
STR-01 | 23/08/2019 | NA |  |  | 3 | Num | 26/08/2019 | 200 Page |  | Materials pending from Admin | 00262 & 26/8/19 | 0 | [8 empty] | From office
STR-01 | 23/08/2019 | NA |  |  | 1 | Pkt | 26/08/2019 | 100 Pcs |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 31-08-2019 | 40 | 40 | 0 | 40 Nos
STR-01 | 23/08/2019 | NA | Register |  | 2 | Num | 26/08/2019 | 200 Page |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 31-08-2019 | 2 | 2 | 0 | From office
STR-01 | 23/08/2019 | NA | Pen Blue |  | 5 | Num | 26/08/2019 |  |  | Materials pending from Admin | 00262 & 26/8/19 | 0 |  |  |  |  | 31-08-2019 | 5 | 5 | 0
STR-01 | 23/08/2019 | NA | Pencil |  | 2 | Num | 26/08/2019 |  |  |  | 00262 & 26/8/19 | 0
STR-01 | 23/08/2019 | NA | Scale Stainless Steel |  | 1 | Num | 26/08/2019 |  |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 31-08-2019 | 1 | 1 | 0
STR-01 | 23/08/2019 | NA | Calculator |  | 1 | Num | 26/08/2019 |  |  |  | 00263 & 26/8/19 | 0 |  |  |  |  | 31-08-2019 | 1 | 1 | 0
STR-01 | 23/08/2019 | NA | Stapler |  | 1 | Num | 26/08/2019 |  |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 31-08-2019 | 1 | 1 | 0
STR-01 | 23/08/2019 | NA | Safety Jacket Fiber Green staff |  | 1 | Num | 23/08/2019 |  |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 2019-08-23 | 1 | 1 | 0
STR-01 | 23/08/2019 | NA | Safety Helmet White |  | 1 | Num | 23/08/2019 |  |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 2019-08-23 | 1 | 1 | 0
STR-01 | 23/08/2019 | NA | Safety Shoe Karam High Ankle fs 21 |  | 1 | Pair's | 23/08/2019 | Size 7 |  |  | 00262 & 26/8/19 | 0 |  |  |  |  | 2019-08-23 | 1 | 1 | 0
EHS - 01 | 26/08/2019 | NA | Leter Head - Acme |  | 1 | Nos | 26/08/2019 |  |  |  | 05767 & 26/8/19 / BLR | 0
Indent Number-01 | 22/08/19 | NA | white board |  | 2 | Nos | 26/08/2019 |  |  |  | 00258 & 22/8/19 | 2 |  | stock transfer |  |  | 31-08-2019 | 2 | 2 | 0
Indent Number-01 | 22/08/19 | NA | white board marker | Blue black green | 3 | Nos | 26/08/2020 |  |  |  | 00258 & 22/8/19 | 3 |  |  |  |  | 31-08-2019 | 3 | 3 | 0 | Black
Indent Number-01 | 22/08/19 | NA | white board duster |  | 2 | Nos | 26/08/2021 |  |  |  | 00258 & 22/8/19 | 2 |  | stock transfer |  |  | 31-08-2019 | 2 | 2 | 0
Indent Number-01 | 22/08/19 | NA | Register | 300 pages | 3 | Nos | 26/08/2022 |  |  |  | 00258 & 22/8/19 | 3 |  |  |  |  | 31-08-2019 | 3 | 3 | 0
Indent Number-01 | 22/08/19 | NA | pen |  | 20 | Nos | 26/08/2023 |  |  |  | 00258 & 22/8/19 | 20 |  |  |  |  | 31-08-2019 | 20 | 20 | 0
Indent Number-01 | 22/08/19 | NA | site instruction book | with carbon | 4 | Nos | 26/08/2024 |  |  |  | 00258 & 22/8/19 | 4 |  |  |  |  | 31-08-2019 | 4 | 4 | 0
Indent Number-01 | 22/08/19 | NA | Box file |  | 10 | Nos | 26/08/2025 |  |  |  | 00258 & 22/8/19 | 8 |  |  |  |  | 31-08-2019 | 10 | 10 | 0
Indent Number-01 | 22/08/19 | NA | Flat file |  | 6 | Nos | 26/08/2026 |  |  |  | 00258 & 22/8/19 | 6 |  |  |  |  | 31-08-2019 | 6 | 6 | 0
Indent Number-01 | 22/08/19 | NA | stapler |  | 1 | Nos | 26/08/2027 |  |  |  | 00258 & 22/8/19 | 1 |  |  |  |  | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | stapler pin |  | 2 | box | 26/08/2028 |  |  |  | 00258 & 22/8/19 | 2 |  |  |  |  | 31-08-2019 | 2 | 2 | 0
Indent Number-01 | 22/08/19 | NA | Table | 4 seater | 2 | Nos | 26/08/2029 |  |  |  | 00258 & 22/8/19 | 2 |  | stock transfer |  |  | 31-08-2019 | 2 | 2 | 0 | Sent to bangalore WH
Indent Number-01 | 22/08/19 | NA | chair |  | 10 | Nos | 26/08/2030 |  |  |  | 00258 & 22/8/19 | 10 |  | stock transfer |  |  | 31-08-2019 | 10 | 7 | 3 | 7 Chairs sent Bangalore WH
Indent Number-01 | 22/08/19 | NA | water dispensor | hot/cold and normal | 1 | Nos | 26/08/2031 |  |  |  | 00258 & 22/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | drinking glass |  | 2 | Nos | 26/08/2032 |  |  |  |  | 0
Indent Number-01 | 22/08/19 | NA | sloted angle rack | 3 feet X 6 feet | 1 | Nos | 26/08/2033 |  |  |  | 00258 & 22/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0 | Using at office container
Indent Number-01 | 22/08/19 | NA | extension box |  | 2 | Nos | 26/08/2034 |  |  |  | 00314 & 17/9/19 | [5 empty] | 20-09-2019 | 2 | 2 | 0 | one using @ store another one with shalendra
Indent Number-01 | 22/08/19 | NA | A4 paper |  | 3 | bundle | 26/08/2035 |  |  |  | 00258 & 22/8/19 | 3 |  |  |  |  | 31-08-2019 | 3 | 3 | 0
Indent Number-01 | 22/08/19 | NA | flask | 5 ltr | 1 | Nos | 26/08/2036 |  |  |  | 00258 & 22/8/19 | 0 | 1 | 00144/23-08-2019 |  |  | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | induction stove |  | 1 | Nos | 26/08/2037 |  |  |  | 00258 & 22/8/19 | 0 | 1 | 00144/23-08-2019 |  |  | 31-08-2019 | 1 | 1 | 0 | Returned to Bangalore WH
Indent Number-01 | 22/08/19 | NA | measurement tape | 30m steel | 1 | Nos | 26/08/2038 |  |  |  | 00258 & 22/8/19 | 0 | 1 | 00142/22-08-2019 | 00051-CHN/19-20 / 26-Aug-2019 | 1 | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | measurement tape | 5m | 6 | Nos | 26/08/2039 |  |  |  | 00258 & 22/8/19 | 3 |  | stock transfer |  |  | 31-08-2019 | 6 | 6 | 0
Indent Number-01 | 22/08/19 | NA | spirit level | big and small | 2 | Nos | 26/08/2040 |  |  |  | 00258 & 22/8/19 | 1 | 1 | 00143/23-08-2019 |  |  | 31-08-2019 | 2 | 2 | 0 | 2 feet 1, 1 feet 1
Indent Number-01 | 22/08/19 | NA | Auto level | with tripod | 1 | Nos | 26/08/2041 |  |  |  | 00288 & 7/9/19 | 0 |  | 00156/07-09-2019
Indent Number-01 | 22/08/19 | NA | plumb bob | heavy duty | 1 | Nos | 26/08/2042 |  |  |  | 00357 & 10/10/19 | 0 | 1 | 00202 & 10-Oct-19 |  |  | 14.10.2019 | 1 | 1 | 0 | Sent to bangalore WH
Indent Number-01 | 22/08/19 | NA | right angle |  | 1 | Nos | 26/08/2043 |  |  |  | 00258 & 22/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | dongle |  | 1 | Nos | 26/08/2044 |  |  |  | 00259 & 22/8/19 | 0 |  |  |  |  | 31-08-2019 | 1 | 1 | 0 | Jio
Indent Number-01 | 22/08/19 | NA | pen drive |  | 1 | Nos | 26/08/2045 |  |  |  | 00258 & 22/8/19 | 0
Indent Number-01 | 22/08/19 | NA | umbrela | big heavy duty | 6 | Nos | 26/08/2046 |  |  |  | 00258 & 22/8/19 | 0 | 6 | 00144/23-08-2019 |  |  | 31-08-2019 | 6 | 6 | 0
Indent Number-01 | 22/08/19 | NA | project ACME stamp |  | 1 | Nos | 26/08/2047 |  |  |  | 00258 & 22/8/19 | 0
Indent Number-01 | 22/08/19 | NA | ink pad |  | 1 | Nos | 26/08/2048 |  |  |  | 00258 & 22/8/19 | 1
Indent Number-01 | 22/08/19 | NA | fan |  | 2 | Nos | 26/08/2049 |  |  |  | 00258 & 22/8/19 | 0 | 2 | 00144/23-08-2019 | 00049-CHN/19-20/ 23-Aug-2019 | 2 | 31-08-2019 | 2 | 2 | 0
Indent Number-01 | 22/08/19 | NA | dairy/note pad | 150 pages | 8 | Nos | 26/08/2050 |  |  |  | 00289 & 7/9/19 | 8
Indent Number-01 | 22/08/19 | NA | dairy/note pad | 30 pages | 10 | Nos | 26/08/2051 |  |  |  | 00258 & 22/8/19 | 10
Indent Number-01 | 22/08/19 | NA | line dori | bundle | 6 | bundle | 26/08/2052 |  |  |  | 00258 & 22/8/19 | 0 |  | 00142 & 22-Aug-2019 | 00053-CHN/19-20 / 26-Aug-2019 | 6 | 31-08-2019 | 6 | 6 | 0
Indent Number-01 | 22/08/19 | NA | marking powder | blue red green | 1 | kg | 26/08/2053 | each colour 1 kg |  |  | 259,260,261 & 22/8/19 | 0 |  | 00142 & 22-Aug-2019 | 00053-CHN/19-20 / 26-Aug-2019 | 1 | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | paint(marking) | blue red green | 1 | kg | 26/08/2054 | each colour 1 kg |  |  | 259,260,261 & 22/8/19 | 0 |  | 00142 & 22-Aug-2019 | 00053-CHN/19-20 / 26-Aug-2019 | 1 | 31-08-2019 | 1 | 1 | 0
Indent Number-01 | 22/08/19 | NA | permanent marker | red/black | 6 | nos | 26/08/2055 | each color |  |  | 00258 & 22/8/19 | 0 |  |  |  |  | 31-08-2019 | 6 | 6 | 0
Indent Number-01 | 22/08/19 | NA | Cupboard-with locker | metalic | 1 | nos | 26/08/2056 |  |  |  | 00258 & 22/8/19 | 1 |  | stock transfer |  |  | 2019-03-09 | 1 |  |  | lock isn't working
EHS - 01 | 20/08/19 | NA | Safety Helmet Yellow | karam | 150 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 150 | 0 | stock transfer |  |  | 31-08-2019 | 150 | 150 | 0
EHS - 01 | 20/08/19 | NA | safety helmet blue | karam | 10 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 10 | 0 | stock transfer |  |  | 31-08-2019 | 10 | 10 | 0
EHS - 01 | 20/08/19 | NA | Safty Helmet Red | karam | 5 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 5 | 0 | stock transfer |  |  | 31-08-2019 | 5 | 5 | 0
EHS - 01 | 20/08/19 | NA | Safety Helmet White visitor | karam | 10 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 9 | 1 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 1 | 31-08-2019 | 10 | 10 | 0
EHS - 01 | 20/08/19 | NA | Safety Goggles white 3 M | 3 M | 300 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 300 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 300 | 31-08-2019 | 300 | 300 | 0
EHS - 01 | 20/08/19 | NA | Nose mask 3 M | 3 M | 300 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 36 | 300 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 300 | 31-08-2019 | 300 | 300 | 0
EHS - 01 | 20/08/19 | NA | Ear Plug |  | 50 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 50 | 0 | stock transfer |  |  | 31-08-2019 | 50 | 50 | 0 | 50 Nos Sent to bangalore WH
EHS - 01 | 20/08/19 | NA | Safety Jacket red strip |  | 40 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 40 | 0 | stock transfer |  |  | 31-08-2019 | 40 | 40 | 0
EHS - 01 | 20/08/19 | NA | Safety Jacket Blue Strip |  | 40 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 40 | 0 | stock transfer |  |  | 31-08-2019 | 40 | 40 | 0
EHS - 01 | 20/08/19 | NA | Safety Jacket White strip |  | 150 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 150 | 0 | stock transfer |  |  | 31-08-2019 | 150 | 150 | 0
EHS - 01 | 20/08/19 | NA | Shoulder pad |  | 25 | Nos | 27.08.2019 |  |  |  | 00253 & 20/8/19 | 0 | 25 | 00140 & 21/08/19 | 00048-CHN/19-20 / 23-Aug-2019 | 25 | 31-08-2019 | 25 | 25 | 0
EHS - 01 | 20/08/19 | NA | Hand Gloves Rubberized anti cut | Level 4 | 300 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 300 | 0 | stock transfer | 00048-CHN/19-20 / 23-Aug-2019 | 276 | 31-08-2019 | 300 | 300 | 0
EHS - 01 | 20/08/19 | NA | Hand Gloves Rubber |  | 150 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 150 | 0 | stock transfer |  |  | 31-08-2019 | 150 | 150 | 0
EHS - 01 | 20/08/19 | NA | Hand Gloves Cotton | Level 5 | 300 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 24 | 276 | ST & 00140 & 21/08/19 |  |  | 31-08-2019 | 300 | 300 | 0
EHS - 01 | 20/08/19 | NA | Electrical gloves | 12 V | 2 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 2 | 00140 & 21/08/19 | 00048-CHN/19-20 / 23-Aug-2019 | 2 | 31-08-2019 | 2 | 2 | 0
EHS - 01 | 20/08/19 | NA | Safety Belt full body double lenyard | Karam | 25 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 25 | 0 | stock transfer |  |  | 31-08-2019 | 25 | 25 | 0 | Returned to Bangalore ware house
EHS - 01 | 20/08/19 | NA | safety shoe | Tiger 7 | 10 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 5 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 5 | 31-08-2019 | 5 | 5 | 0
EHS - 01 | 20/08/19 | NA |  | 8 | 10 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 7 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 7 | 31-08-2019 | 7 | 7 | 0
EHS - 01 | 20/08/19 | NA |  | 9 | 10 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 6 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 6 | 31-08-2019 | 6 | 6 | 0
EHS - 01 | 20/08/19 | NA |  | 10 | 10 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 10 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 10 | 31-08-2019 | 10 | 10 | 0
EHS - 01 | 20/08/19 | NA | Gum Boot | 8 | 3 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 3 | 3 | 00143/23-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 3 | 31-08-2019 | 3 | 3 | 0
EHS - 01 | 20/08/19 | NA |  | 9 | 10 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 1 | 6 | 00143/23-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 6 | 31-08-2019 | 6 | 6 | 0
EHS - 01 | 20/08/19 | NA |  | 10 | 5 | Pair | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 4 | 1 | 00143/23-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 1 | 31-08-2019 | 1 | 1 | 0
EHS - 01 | 20/08/19 | NA | Safety Poster |  | 55 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 55 | 00140/21-08-2019 | 00047-CHN/19-20 / 22-Aug-2019 | 55 | 31-08-2019 | 54 | 35 | 15
EHS - 01 | 20/08/19 | NA | Safety statistics board |  | 1 | Nos | 27.08.2019 |  |  |  | 00251 & 27/8/19 | 1 | 0 | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0
EHS - 01 | 20/08/19 | NA | safety Park |  | 1 | Nos | 27.08.2019 |  |  |  | 00251 & 20/8/19 | 1 | 0 | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0
EHS - 01 | 20/08/19 | NA | Induction sticker |  | 400 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 | 400 | 00140/21-08-2019 | 00047-CHN/19-20 / 22-Aug-2019 | 400 | 31-08-2019 | 400 | 400 | 0
EHS - 01 | 20/08/19 | NA | Scaffold tag |  | 100 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 0 |  | 00140/21-08-2019 | 00047-CHN/19-20 / 22-Aug-2019 | 100 | 31-08-2019 | 100 | 100 | 0
EHS - 01 | 20/08/19 | NA | scaffold tag red |  | 20 | Nos | 27.08.2019 |  |  |  | 00249 & 20/8/19 | 20 | 0 | stock transfer |  |  | 31-08-2019 | 20 | 20 | 0
EHS - 01 | 20/08/19 | NA | fire extingusher dcp |  | 10 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 9 | 0 | 00146 & 27-Aug-2019 | 00056-CHN/19-20 / 27-Aug-2019 | 9
EHS - 01 | 20/08/19 | NA | fire extinghusher co2 |  | 10 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 10 | 0 | 00146 & 27-Aug-2019 | 00056-CHN/19-20 / 27-Aug-2019 | 10
EHS - 01 | 20/08/19 | NA | safety cone |  | 30 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 30 | 0 | stock transfer |  |  | 31-08-2019 | 30 | 30 | 0
EHS - 01 | 20/08/19 | NA | fire bucket with stand |  | 6 | Set | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 3 | 3 | 00141/22-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 3 | 31-08-2019 | 6 | 5 | 1
EHS - 01 | 20/08/19 | NA | Clear face shield |  | 5 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 0 | 5 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 5 | 31-08-2019 | 5 | 5 | 0
EHS - 01 | 20/08/19 | NA | Welding Face Shield |  | 2 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 2 | 1 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 1 | 31-08-2019 | 1 | 1 | 0
EHS - 01 | 20/08/19 | NA | Fire blanket |  | 2 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 2 | 0 | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0
EHS - 01 | 20/08/19 | NA | Welding Apron |  | 2 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 1 | 1 | 00140/21-08-2019 | 00048-CHN/19-20 / 23-Aug-2019 | 1 | 31-08-2019 | 2 | 2 | 0
EHS - 01 | 20/08/19 | NA | Barrication Tape |  | 10 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 10 | 0 | stock transfer |  |  | 31-08-2019 | 10 | 10 | 0
EHS - 01 | 20/08/19 | NA | Welding lether Gloves |  | 2 | Pair | 27.08.2019 |  |  |  | 00251 & 27/8/19 | 2 | 0 | stock transfer |  |  | 31-08-2019 | 2 | 2 | 0
EHS - 01 | 20/08/19 | NA | Surgical Gloves |  | 100 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 100 | 0 | stock transfer |  |  | 31-08-2019 | 100 | 100 | 0
EHS - 01 | 20/08/19 | NA | Full Body appron -plastic |  | 25 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 2 | 23 | 00140/21-08-2019 |  |  | 31-08-2019 | 23 | 23 | 0 | 23 Nos Sent to bangalore WH
EHS - 01 | 20/08/19 | NA | First Aid Box with medicine |  | 2 | Box | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 2 | 0 | stock transfer |  |  | 31-08-2019 | 2 | 2 | 0 | Received medicine only
EHS - 01 | 20/08/19 | NA | Dustbin Green |  | 6 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 5 | 5 | 0 | 5 Nos sent to bangalore WH
EHS - 01 | 20/08/19 | NA | Dustbin Red |  | 6 | Nos | 27.08.2019 |  |  |  | 00251 & 20/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 5 | 5 | 0 | 5 Nos sent to bangalore WH
EHS - 01 | 20/08/19 | NA | Dustbin Blue |  | 6 | Nos | 27.08.2019 |  |  |  | 00251 & 27/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 6 | 5 | 1 | 5 Nos sent to bangalore WH
EHS - 01 | 20/08/19 | NA | Green Net ( Dust net ) | 2m W x 30m L | 50 | Mtr | 27.08.2019 |  |  |  | 00251 & 20/8/19 | 0 |  | 00140/21-08-2019 |  |  | 13-09-2019 | 1 | 1 | 0
EHS - 01 | 20/08/19 | NA | Mega Phone |  | 1 | Nos | 27.08.2019 |  |  |  | 00250 & 20/8/19 | 1 | 0 | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0 | Sent to Bangalore WH
EHS - 01 | 20/08/19 | NA | breathalyzer alcohol tester |  | 1 | Nos | 27.08.2019 |  |  |  | 00251 & 27/8/19 | 1 | 0 | stock transfer |  |  | 31-08-2019 | 1 | 1 | 0 | Sent to Bangalore WH
EHS - 01 | 20/08/19 | NA | Life Line Rope | 12 MM | 20 | Mtr | 27.08.2019 |  |  |  | 00250 & 20/8/19 | 0 |  | 00149/29-Aug-2019
EHS - 01 | 20/08/19 | NA | ID Card Pouch |  | 400 | Nos | 27.08.2019 |  |  |  | 00251 & 27/8/19 | 140 | 260 | 00143/23-Aug-2019 |  |  | 31-08-2019 | 140 | 140 | 0
EHS - 01 | 20/08/19 | NA | Lanyard yellow |  | 150 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 150 |  | stock transfer |  |  | 31-08-2019 | 150 | 150 | 0
EHS - 01 | 20/08/19 | NA | Lanyard Red |  | 50 | Nos | 27.08.2019 |  |  |  | 00250 & 27/8/19 | 50 |  | stock transfer |  |  | 31-08-2019 | 50 | 50 | 0
EHS - 01 | 20/08/19 | NA | Lanyard Blue |  | 50 | Nos | 27.08.2019 |  |  |  | 00251 & 27/8/19 | 50 |  | stock transfer |  |  | 31-08-2019 | 50 | 50 | 0
EHS - 01 | 20/08/19 | NA | Mustroll |  | 1 | Nos | 27.08.2019 |  |  |  | 00250 & 20/8/19 | 1 |  | stock transfer |  |  | 31-08-2019 | 1
EHS - 01 | 20/08/19 | NA | Register | 300 page | 3 | Nos | 27.08.2019 |  |  |  | 00250 & 20/8/19 | 0 |  |  |  |  | 31-08-2019 | 3 | 3 | 0
EHS - 01 | 20/08/19 | NA | Register | 100 page | 2 | Nos | 27.08.2019 |  |  |  | 00250 & 20/8/19 | 2 |  |  |  |  | 31-08-2019 | 2 | 2 | 0
EHS - 01 | 20/08/19 | NA | Box File |  | 4 | Nos | 27.08.2019 |  |  |  | 00250 & 20/8/19 | 0 |  |  |  |  | 31-08-2019 | 4 | 4 | 0
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +ravi.sl@acmeinteriors.co.in +sudhan.gunagi@acmeinteriors.co.in Please update the same ASAP. _Assigned to Ravi SL_ -Wilma Pereira _Marked as done_ -Ravi SL _Re-opened_ -Ravi SL
Note on T4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +ravi.sl@acmeinteriors.co.in +sudhan.gunagi@acmeinteriors.co.in I dont see any of the materials are being issued, without that how the work is happening? _Assigned to Ravi SL_ -Wilma Pereira Ma'am some materials are issued, by tomorrow "EOD ISSUED QUANTITY " will be updated without fail. -Sudhan Gunagi why cant the same updated the time od issuing the material. Please do it today without fail. -Wilma Pereira
Note on M40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 feet provide -Ravi SL
Note on M86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: shifted from Chennai warehouse -Ravi SL
Note on M87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shifted from Chennai warehouse -Ravi SL
Note on M99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Balance qty to be provide from warehouse once rectification done -Ravi SL
Note on M100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Balance qty to be provide from warehouse once rectification done -Ravi SL
Note on M101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Balance qty to be provide from warehouse once rectification done -Ravi SL

## Technical Submittal
TECHNICAL SUBMITTALS & APPROVAL STATUS
[9 empty] | R0 |  |  | R1 |  |  | R2
S.No. | BOQ No. | LIST OF ITEMS FOR WHICH TECHINICAL DETAILS TO BE SUBMITTED FOR APPROVAL | MAKE/MODEL AS PER BOQ | MAKE/MODEL REQUIRED TO BE INSTALLED | ANY COST IMPACT DUE TO THE CHANGE IN MAKE/MODEL? | DATE OF SUBMISSION | APPROVAL STATUS BY CONSULTANT | DATE OF APPROVAL / COMMENT FROM CONSULTANT | DATE OF RESUBMISSION INCORPORATING COMMENTS | APPROVAL STATUS OF RESUBMITTED DRAWING BY CONSULTANT | DATE OF APPROVAL / COMMENT FROM CONSULTANT | DATE OF RESUBMISSION INCORPORATING COMMENTS | APPROVAL STATUS OF RESUBMITTED DRAWING BY CONSULTANT | DATE OF APPROVAL / COMMENT FROM CONSULTANT | DATE OF RESUBMISSION INCORPORATING COMMENTS | APPROVAL STATUS OF RESUBMITTED DRAWING BY CONSULTANT | DATE OF APPROVAL / COMMENT FROM CONSULTANT | REMARKS FROM PROJECT MANAGER
Electrical
1 | Electrical BOQ-B.1 | LT cables | FINOLEX / RR CABLES / KEI / POLYCAB | KEI | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
2 | Electrical BOQ-A.1 | DB | SIEMENS | SIEMENS | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA |  |  |  | All circuit breakers and Isolators are also from Siemens
3 | Electrical BOQ-12,AD.1 | MS and GI conduits | SUPEME /AKG /BEC | BEC | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
4 | ELectrical BOQ-E.E1.to 19 | 1* 32W / [4*8W] LED Based Light fixture | Philips/Wipro | Lighting technologies |  | 22-08-2019 | Rejected | 26-08-2019 | TBC | TBC | TBC |  |  | TBC |  |  |  | Lighting technologies approved
5 | Electrical BOQ-B | Lugs and glands | DOWELS / SMI / JAINSONS / COMET | Dowells | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
6 | Electrical BOQ-7 | FRLS conduit | PRECISION / AVON / VIP | VIP | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
7 | Electrical BOQ- C.5 to11 | Raceways and cabletrays | OBO INDIA / PUKE India/ NIDEAX India / PRAKASH FABCON | NIDEAX | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
8 | Electrical BOQ -D6 | Industrial Plug & sockets | NEPTUNE / SCHNEIDER / GEWISS/ LEGRAND/ SCAME | Neptune-Bals | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
9 | Electrical BOQ-D6 to 10 | Switch and Socket | LEGRAND/ CRABTREE | Legrand Myrius | NO | 22-08-2019 | Approved | 2019-10-16 | NA | NA | NA |  |  | NA
10 | Electrical BOQ-D. (1,1.1).2(2.2).3,4, 5.(5.1) | Wires | FINOLEX / RR CABLES / KEI / POLYCAB | KEI | NO | 22-08-2019 | Approved | 26-08-2019 | NA | NA | NA |  |  | NA
11 | Electrical BOQ-H8 | Rubber mats | COMMERCIAL ENTERPRISES / DL MILLER & CO. LTD. / PREMIER POLYFILM LTD. / RMG POLYVINYL INDIA LTD. | Philips | NO | 19-09-2019 | Submitted
12 | ELectrical BOQ-E15 | PIR sensors | No make | Deep jyoti rubber(volt mat) | NO | 19-09-2019 | Submitted
HVAC
1 | HVAC BOQ-1 | AIR HANDLING UNIT | Flaktwood/Systemair/Zeco/Citizen | Zeco |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Rejected | 17-09-2019 | 20-09-2019 | Pending | Pending | 2019-10-16 | Approved | 2019-10-18
2 | HVAC BOQ-1 | FILTER | Fraudenberg / American Air filter(AAF)/ Camfil | American air filter |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Rejected | 17-09-2019 | NA | NA | NA | 2019-10-16 | Approved | 2019-10-18
3 |  | INLINE /Cabinet EXHAUST/FA FAN | Kruger/Systemair/Caryaire | Carryaire |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Rejected | 17-09-2019 | 20-09-2019 | Rejected | 20-9-2019 | 21-09-2019 | Approved | 23-09-2019 | CFM values to be mentioned
4 |  | GALVANIZED SHEET STEEL | Jindal / TATA | Jindal |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
5 |  | FACTORY FABRICATED DUCTS | Radiant/Rolastar | Rolastar |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Rejected | 17-09-2019 | 20-09-2019 | Approved | 20-09-2019 |  |  |  | Rejected as the selected Equipment/Material was not highlighte din the Spec sheet.
|  | Factory fabricated elliptical ducts | No make | GP SPIRA |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Rejected | 17-09-2019 | 20-09-2019 | Rejected | 20.09.2019 | No resubmission previous submission considered | Approved | 26.09.2019 | JAYCE to discussw ith JACOBS for GP SPIRA
6 |  | GRILLES | Caryaire / Systemaire /cosmos/Ruskin | Cosmos |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved except linear grilles | 17-09-2019 | 20-09-2019 | Approved | 20-09-2019
7 |  | SQUARE DIFFUSER | Caryaire / Systemaire /cosmos/Ruskin | Cosmos |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | approved | 17-09-2019 | NA | NA | NA
8 |  | SLOT DIFFUSERS | Caryaire / Systemaire /cosmos/Ruskin | Cosmos |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | approved | 17-09-2019 | NA | NA | NA
9 |  | VOLUME CONTROL DAMPER | Caryaire / Systemaire /cosmos/Ruskin | Cosmos |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | approved | 17-09-2019 | NA | NA | NA
10 |  | MOTORIZED FIRE DAMPER | Caryaire / Systemaire /cosmos/Ruskin | Cosmos |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | approved | 17-09-2019 | NA | NA | NA
11 |  | ACTUATOR | Belimo | Belimo |  | 22-08-2019 | Approved | 27-08-2019 | NA | NA | NA | NA | NA | NA
12 |  | THERMAL INSULATION | Armaflex | Armaflex |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
13 |  | ACOUSTIC INSULATION | Armaflex | Armaflex |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
14 |  | MS PIPE | Jindal / TATA | Jindal |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
15 |  | 2-WAY CONTROL VALVE | Honeywell | Honeywell |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Descoped | 17-09-2019 | NA | NA | NA
16 |  | BUTTERFLY VALVE | Audco | Audco |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Descoped | 17-09-2019 | NA | NA | NA
17 |  | BALANCING VALVE | Advance | Advance |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Descoped | 17-09-2019 | NA | NA | NA
18 |  | BALL VALVE | Audco | Audco |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Descoped | 17-09-2019 | NA | NA | NA
19 |  | AUTO AIR VENT | Anergy | Anergy |  | 22-08-2019 | Approved | 27-08-2019 | NA | NA | NA | NA | NA | NA
20 |  | FLEXIBLE DUCT | no make | Alpha star |  | 2019-10-16
21 |  | PRESSURE GAUGE | Waree/H.Guru | Waree |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
22 |  | TEMPERATURE GAUGE | Waree / H.Guru | Waaree |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
23 |  | Y-STRAINER | Sant | Sant |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Descoped | 17-09-2019 | NA | NA | NA
24 |  | CABLE | Polycab / Gloster / INCAB | Polycab |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | pending | 17-09-2019 | NA | NA | NA
25 |  | THERMOSTAT | Honeywell | Honeywell |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
26 |  | DUCT PRESSURE SENSOR | Honeywell | Honeywell |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | pending | 17-09-2019 | NA | NA | NA
27 |  | DX TYPE Hi-Wall UNIT | Carrier / Daikin / Hitachi | Daikin |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Rejected | 17-09-2019 | 20-09-2019 | Rejected | 20-09-2019 | 21-09-2019 |  |  | Specs dont match BOQ, Revision required.
28 |  | CASSETTE UNITS | Carrier / Daikin / Hitachi | Daikin |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA | 21-09-2019
29 |  | VARIABLE AIR VOLUME UNITS | Trox / Honeywell (Phoenix) | Honeywell |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | One make to be proposed | 17-09-2019 | 20-09-2019 | Approved | 20-09-2019
30 |  | VRFSYSTEM | Bluestar/O-General/Media | Daikin |  | 22-08-2019 | Rejected | 27-08-2019 | 2019-12-09 | Approved | 17-09-2019 | NA | NA | NA
31 |  | VAV bacnet gateway controller | Honeywell | Honeywell |  | 2019-10-16 | Pending Approval
32 |  | TOuch screen with controller for VAV |  |  |  |  | pending Submission
33 |  | CAT 6 cable | No make | D link |  | 2019-10-16 | Pending Approval
34 |  | EX and FA vav controller | Honeywell | Honeywell |  | 2019-10-16 | Pending Approval
35 |  | Master controller for EX and FA vav with modbus | Honeywell | Honeywell |  | 2019-10-16 | Pending Approval
36 |  | Corded and cordless remotes for VRF based AHU | Daikin | Daikin |  | 2019-10-16 | Pending Approval
37 |  | CRC for VRF based AHU | Daikin | Daikin |  | 2019-10-16 | Pending Approval
38 |  | Bacnet adaptor for VRF based AHU | Daikin | Daikin |  | 2019-10-16 | Pending Approval
39 |  | I touch manager for VRF based AHU | Daikin | Daikin |  | 2019-10-16 | Pending Approval
40 |  | starter panel for EX /FA fan | No make |  |  |  | pending Submission
41 |  | Push button stations | No make | L&T |  | 2019-10-16 | Pending Approval
42 |  | VFD | ABB | ABB |  | 2019-10-16 | Pending Approval
43 |  | Starte Panel for AHU,TFA, EX fan and air washer unit. |  |  |  |  | pending Submission
44 |  | Cable tray | NA | IMAI |  | 2019-10-22 | Approval Pending
45 |  | copper pipe | NA | MEXFLOW |  | 2019-10-22 | Approval Pending
46 |  | drain pipe | NA | Supreme CPVC |  | 2019-10-22 | Approval Pending
47 |  | drain pump | ASPEN | ASPEN |  | 2019-10-22 | Approval Pending
48 |  | TFA | Daikin | Daikin |  | 2019-10-22 | Approval Pending
PHE
1 | PHE BOQ -A1,A2,A3 | PPR Pipes | Supreme / Prince / Ashirvad | Supreme | NO | 2019-09-03 | Approved | 2019-09-04 | NA | NA | NA |  |  | NA
2 | PHE BOQ -B1,B3,B4 | uPVC SWR Type B pipes | Supreme / Prince / Ashirvad | Supreme | NO | 2019-09-03 | Approved | 2019-09-04 | NA | NA | NA |  |  | NA
3 | PHE BOQ-B13 | DWC HDPE pipes | Supreme / REX | Supreme | NO | 2019-09-03 | Approved | 2019-09-04 | NA | NA | NA |  |  | NA
4 | PHE BOQ-B2 | uPVC high pressure pipes | Supreme / Kisan | Supreme | NO | 2019-09-03 | Approved | 2019-09-04 | NA | NA | NA |  |  | NA
5 | PHE BOQ-A10 | Instant heater | Stiebel eltron or equivalent | Jaquar |  | 2019-10-04 | Approved | 2019-10-05
6 | PHE BOQ-A4 | Ball valves | Zoloto / Lehry / Audco | Zoloto |  | 2019-10-04 | Approved | 2019-10-05
7 | PHE BOQ-B8 | Floor clean out | Supreme / Prince / Ashirvad | Chilly |  | 2019-10-04 | Approved | 2019-10-05
8 | PHE BOQ-B14,B16 | FRP manhole cover | Thermodrain | Thermodrain |  | 2019-10-04 | Approved | 2019-10-05
9 | PHE BOQ-B21 | Grease trap | No make mentioned | Nu green |  | 2019-10-04 | Approved | 2019-10-05
10 | PHE BOQ-B14 | Ptrap | Supreme / Prince / Ashirvad | Supreme |  | 2019-10-04 | Approved | 2019-10-05
11 | PHE BOQ-B9 | SS grating | Chilly | Chilly |  | 2019-10-04 | Approved | 2019-10-05
12 | PHE BOQ-B6 | Multitrap | Supreme / Prince / Ashirvad | Supreme |  | 2019-10-04 | Approved | 2019-10-05
13 | PHE BOQ-B7 | Nahni trap | Supreme / Prince / Ashirvad | Supreme |  | 2019-10-04 | Approved | 2019-10-05
14 | PHE BOQ-A1 | Anchor Fastner & Rod (Hi-Tech Support) | Rapidrop / Hilti / Chili / Fischer | Fischer |  | 2019-10-04 | Approved | 2019-10-05
15 | PHE BOQ-A19 | Inline booster system | Grundfos | Grundfos |  | 2019-10-14 | approved | 2019-10-22 | [9 empty] | logic and SLD to be submitted post PO
16 | PHE BOQ-B5 | Air admittance valve | Studor / Ashirvad | TBC |  |  | pending Submission
17 | PHE BOQ-A9 | AIr release valve | Zoloto / Lehry / Audco | Zoloto |  | 2019-10-04 | Approved | 2019-10-05
18 | PHE BOQ-A16 | Butterfly valve | Zoloto / Lehry / Audco | Zoloto |  | 2019-10-04 | Approved | 2019-10-05
19 | PHE BOQ-A19 | Y strainer | Zoloto / Lehry / Audco | Zoloto |  | 2019-10-05 | Approved | 2019-10-05
20 | PHE BOQ-A19 | Non Return valve | Zoloto / Lehry / Audco | Zoloto |  | 2019-10-05 | Approved | 2019-10-14
21 | NT | Floor drain for labs | Astra | Astr |  | 2019-10-16 | Approved | 2019-10-30
22 | NT | Water flow meter | ASCORP | ASCORP |  | 2019-11-06 | Pending Approval
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +sibin@acmeinteriors.co.in Please update the current status. _Assigned to sibin_ -Wilma Pereira

## Drawing Register
DRAWING REGISTER
Whenever a drawing is revised and a drawing revision is issued, the old drawing No. should be highlighed in the register and the same must be collected from the project team and should IMMEDIATELY be removed from the site and submitted in the office, for the purpose records.
S.No. | LIST OF ITEMS FOR WHICH DRAWINGS/DETAILS ARE REQUIRED FROM CONSULTANT | Details of Drawings received |  |  |  | Issue 1 |  |  | Issue 2 |  |  |  | Issue 3 |  |  |  | Issue 4
|  | Trade - ( Specify C&I, FAPA, ELECTRICAL, HVAC, PLUMBING etc.) | Drawing Number | Drawing Title | Format (Specify CAD, PDF or PRINTOUTS) | Revision No | Drawing Date | Recieved On | Revision No | Drawing Date | Recieved On | OLD Drawing removed from site? Yes/No | Revision No | Drawing Date | Recieved On | OLD Drawing removed from site? Yes/No | Revision No | Date | Recieved On | OLD Drawing removed from site? Yes/No
1 |  | Electrical | IFF/SC/AP/LAB/S-01 | IFF- LAB DB -SLD | PDF | R0 | 2019-02-01 | 2019-08-06
2 |  | Electrical | IFF/SC/AP/ADMIN/FL-01 | IFF-FLAVORS-ADMIN-SLD | PDF | R0 | 2019-02-01 | 2019-08-06 | R3 | 15-05-2019 | 23-08-2019 |  | R4 | 2019-09-03 | 2019-09-03
3 |  | Electrical | IFF/SC/AP/ADMIN/FR-01 | IFF-FRAGRANCE-ADMIN-SLD | PDF | R0 | 2019-02-01 | 2019-08-06 | R3 | 16-05-2019 | 23-08-219 |  | R4 | 2019-09-03 | 2019-09-03
4 |  | Electrical | 150_00-401_A1 | LIGHTING LAYOUT-FLAVOURS ADMIN | AutoCAD | R1 | Not mentioned in Drawing | 2019-08-12
5 |  | Electrical | 150_00-403_A3 | LIGHTING LAYOUT PLAN-FG WARE HOUSE OFFICE | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
6 |  | Electrical | 150_00-404_A4 | LIGHTING LAYOUT- RM WAREHOUSE OFFICE FL_ | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
7 |  | Electrical | 150_00-405_A5 | LIGHTING LAYOUT -PRODUCTION OFFICE (POWDER) | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
8 |  | Electrical | 150_00-407_B10 | LIGHTING LAYOUT - FG PM STORE | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
9 |  | Electrical | 150_00-408_B11 | LIGHTING LAYOUT-PRODUCTION OFFICE FR_ | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
10 |  | Electrical | 150_00-409_C12 | LIGHTING LAYOUT- MAINTANANCE OFFICE | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
11 |  | Electrical | 150_00-410_C13 | LIGHTING LAYOUT-SECURITY OFFICE | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
12 |  | Electrical | 150_00-501-B7 | LIGHTING LAYOUT-ADMIN FRAGRANCE | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
13 |  | Electrical | 150_01-402_A2 | REFLECTED CEILING PALN-QC LAB FLAVOURS | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12
14 |  | Electrical | 150_01-406_A6 | LIGHTING LAYOUT-PRODUCTION OFFICE (LIQUID) | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
15 |  | Electrical | 150_01-501-B9 | LIGHTING LAYOUT - QC LAB _MCC_FR | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
16 |  | Electrical | 150_02-501-B8 | LIGHTING LAYOUT PLAN-PIA LAB_FR | AutoCAD & PDF | R1 | Not mentioned in Drawing | 2019-08-12 | R0-WIP | 2019-08-23 | 2019-08-23
17 |  | Electrical | 150_501_A1 | A1-IFF- FLAVOR- ADMIN- LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
18 |  | Electrical | IFF/CHN/FL/QA+QC-1 | A2-IFF- FLAVOR- LIQUID+QA- QC- LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
19 |  | Electrical | 150_501_A3 | A3 - IFF - FLAVOR-WAREHOUSE -FG PM STORE-GF- LTG -R3 | AutoCAD | R3 | 2019-05-11 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
20 |  | Electrical | 150_501_A4 | A4 - IFF -FLAVOR -WAREHOUSE OFFICE-RM STORE- LTG-R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
21 |  | Electrical | 150_501_A5 | A5 - IFF- FLAVOR- PRODUCTION OFC- INSP QC-GF- LTG -R3 | AutoCAD | R3 | 2019-08-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
22 |  | Electrical | 150_501_A6 | A6 - IFF -FLAVOR - PRODUCTION OFFICE -FF- LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
23 |  | Electrical | 150_501_B7 | B7 -IFF -FRAGRANCE -ADMIN- GF -LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
24 |  | Electrical | 150_501_B8 | B8 - IFF - FRAGRANCE - PIA LAB - LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
25 |  | Electrical | 150_501_B9 | B9 - IFF - FRAGRANCE - QC LAB- MCC-LTG-R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
26 |  | Electrical | 150_501_B10 | B10- IFF -FRAGRANCE PM STORE-SAMPLING -WEIGHING -LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
27 |  | Electrical | 150_501_B11 | B11 - IFF -FRAGRANCE - IPQC LAB - LTG -R3 | AutoCAD | R3 | 2019-08-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
28 |  | Electrical | IFF/CHN/FL/MO-SY-1 | C12 - IFF - SCRAP YARD - MAINTAINANCE OFFICE - LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
29 |  | Electrical | 150_501_C13 | C13 - IFF - SECURITY- OFFICE -LTG -R3 | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
30 |  | Electrical | 150_503_A1 | Power Point Layout Admin | AutoCAD | R3 | 2019-07-06 | 2019-08-12 | R4.1 | 2019-07-29 | 2019-08-23
31 |  | Electrical | 150_504/05_A1 | UnderFloor trunk/Overhead tray layout for admin | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4.1 | 2019-07-29 | 2019-08-23
32 |  | Electrical | IFF/CHN/FL/QA+QC-2 | UnderFloor trunk/Overhead tray layout for Liquid+QA-QC Lab | AutoCAD | R3 | 2019-07-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
33 |  | Electrical | IFF/CHN/FL/QA+QC-3 | UnderFloor trunk/Overhead tray layout for Liquid+QA-QC Lab( Actually depicts the power layout- name seems to be wrong) | AutoCAD | R3 | 2019-07-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
34 |  | Electrical | 150_504/5_A3 | Trunking/OH cable tray/power point layout for warehouse FG PM store | AutoCAD | R3 | 2019-07-06 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
35 |  | Electrical | 150_503_A3 | Power point layout for warehouse FG PM store | AutoCAD | R3 | 2019-07-06 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
36 |  | Electrical | 150_5034/5_A4 | Trunking/OH cable tray/power point layout for office /RM store | AutoCAD | R3 | 2019-07-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
37 |  | Electrical | 150_501-A5 | Trunking/OH cable tray /power point layout for production office/insp.QC | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
38 |  | Electrical | 150_503/4/5_A6 | Trunking/OH cable tray /Power point layout for production office(FF) | AutoCAD | R3 | 2019-08-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
39 |  | Electrical | 150_503_A7(150_503_B7) | Power point Layout for Ground Floor | AutoCAD | R3 | 2019-08-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
40 |  | Electrical | 150_504/5_B7 | Underfloor Trunk/overhead tray layout for Ground Floor | AutoCAD | R2 | 2019-05-12 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
41 |  | Electrical | 150_503/4-B8 | Underfloor Trunk/overhead tray layout for PIA Lab[SF] | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
42 |  | Electrical | 150_503_B8 | Underfloor Trunk/overhead tray layout for PIA Lab[SF]( This layout is a power layout-seems like a naming error) | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R3 | 2019-07-08 | 2019-08-12
43 |  | Electrical | 150_503/4/5_B9 | underfloor Trunk/Overhead tray/Power point layout for QC-Lab-MCC( Contains only the trunking layout) | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
44 |  | Electrical | 150_503/4/5_B10 | Trunking/Power point layout for FG store/Sampling/Weighing [GF]( only the Power layout) | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
45 |  | Electrical | 150_503/3/4/5_B11 | Trunking/Power point layout for IPQC lab( only power layout) | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
46 |  | Electrical | 150_503/4/5_C12 | Trunking/Power point layout for Maintenance office(Scrap yard)( only power layout) | AutoCAD | R3 | 2019-07-08 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
47 |  | Electrical | 150_503/4/5_C13 | Trunking/Power point layout for Security office( only Power layout) | AutoCAD | R3 | 2019-08-07 | 2019-08-12 | R4 | 2019-07-20 | 2019-08-23
48 |  | HVAC | IIF-HVAC-01 | 00-101_A1 FLAVOURS ADMIN HVAC LAYOUT- 1 | AutoCAD | R2 | 2019-02-04 | 2019-08-12 | R3 | 2019-08-20 | 2019-08-23 |  | R4 | 2019-08-30 | 2019-09-06
49 |  | HVAC | IFF-HVAC-A2 QC | 01-101 A2_ FLAVOURS QC LAB 1ST FLOOR | AutoCAD | R3 | 2019-02-04 | 2019-08-12 | R5 | 2019-08-14 | 2019-08-23 |  | R6 | 2019-08-30 | 2019-09-06
50 |  | HVAC | IFF-HVAC-B9 | 02.(19.08.2019) B9 FRAGRENCE MCC LAB | AutoCAD | R2 | 2019-03-14 | 2019-08-12 | R4 | 2019-08-20 | 2019-08-23 |  | R4 | 2019-08-20 | 2019-09-06
51 |  | HVAC | IFF-HVAC-B8 | 02-101-B8 FRAGRANCE PIA LAB HVAC LAYOUT | AutoCAD | R3 | 2019-02-04 | 2019-08-12 | R4 | 2019-08-19 | 2019-08-23 |  | R6 | 2019-09-06 | 2019-09-06
52 |  | HVAC | IFF-HVAC-B7 | B7-HVAC LAYOUT- ADMIN FLOOR | AutoCAD | R3 | 2019-02-04 | 2019-08-12 | R5 | 2019-08-06 | 2019-08-23 |  | R6 | 2019-09-06 | 2019-09-06 |  | R7 | 2019-10-18 | 2019-10-19
53 |  | PHE | 19-IFF-PL-101 | 101-Sewer Drainage Layout at Ground Floor | AutoCAD | R0 | 2019-03-14 | 2019-08-12 | R2 | 2019-08-10 | 2019-08-23
54 |  | PHE | 19-IFF-PL-300 | 300-Internal Plumbing Layour for Admin Fragnance- 3 drawings | AutoCAD | R0 | 2019-03-14 | 2019-08-12 | R2 | 2019-08-10 | 2019-08-23
55 |  | PHE | 19-IFF-PL-301 | 301-Internal Plumbing Layout at Pia Lab Fragnance | AutoCAD | R0 | 2019-03-14 | 2019-08-12 | R2 | 2019-08-10 | 2019-08-23
56 |  | PHE | 19-IFF-PL-302 | 302-Internal Plumbing Layout at Admin Interior Layout Flavors-2 drawings | AutoCAD | R1 | 2019-03-14 | 2019-08-12 | R3 | 2019-08-10 | 2019-08-23
57 |  | PHE | 19-IFF-PL-303 | 303-Internal Plumbing Layout at Maintainance Office | AutoCAD | R0 | 2019-03-14 | 2019-08-12 | R3 | 2019-08-10 | 2019-08-23
58 |  | PHE | 19-IFF-PL-304 | 304-Internal Plumbing Layout at Security Office | AutoCAD | R0 | 2019-03-14 | 2019-08-12 | R3 | 2019-08-10 | 2019-08-23
59 |  | C&I | 150_101.12_A1 | 101.12_A1 A1 IT ROOM FLAVOURS ADMIN | AutoCAD | R0 | 2019-08-12 | 2019-08-12
60 |  | C&I | 150_101.2_A1 | 102.2_A1 PARTITION SETOUT I.T. ROOM FLAVOURS ADMIN | AutoCAD | R0 | 2019-08-12 | 2019-08-12
61 |  | C&I | 00-103_A1 | FLOORING LAYOUT- ADMIN FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
62 |  | C&I | 00-103_A3 | FLOORING LAYOUT- WAREHOUSE OFF+ SAMPLING FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
63 |  | C&I | 00-103_A4 | FLOORING LAYOUT- WAREHOUSE OFFICE FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
64 |  | C&I | 00-103_A5 | FLOORING LAYOUT- PRODUCTION OFFICE (POWDER) FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
65 |  | C&I | 00-103_B10 | FLOORING LAYOUT- WAREHOUSE OFF +SAMPLING LAB FR_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
66 |  | C&I | 00-103_B11 | FLOORING LAYOUT- PRODUCTION OFFICE FR_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
67 |  | C&I | 00-103_C12 | FLOORING LAYOUT-MAINTAINANCE OFFICE | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
68 |  | C&I | 00-103-B7 | FLOORING LAYOUT -ADMIN FR_ | AutoCAD & PDF | R0 | 13/07/2019 | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
69 |  | C&I | 00-104_C13 | FLOORING LAYOUT-SECURITY OFFICE | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
70 |  | C&I | 01-103_A2 | FLOORING LAYOUT-QC LAB FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
71 |  | C&I | 01-103_A6 | FLOORING LAYOUT- PRODUCTION OFFICE (LIQUID) FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
72 |  | C&I | 01-103-B9 | FLOORING LAYOUT-QC LAB _MCC_FR | AutoCAD & PDF | R0 | 13/07/2019 | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
73 |  | C&I | 02-103-B8 | FLOORING LAYOUT-PIA LAB_FR | AutoCAD & PDF | R0 | 13/07/2019 | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
74 |  | C&I | 00-104_A1 | CEILING LAYOUT- ADMIN FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
75 |  | C&I | 00-104_A3 | CELING LAYOUT- WAREHOUSE OFF+ SAMPLING LAB FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
76 |  | C&I | 00-104_A4 | CEILING LAYOUT- WAREHOUSE OFFICE FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
77 |  | C&I | 00-104_A5 | CEILING LAYOUT- PRODUCTION OFFICE (POWDER) FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
78 |  | C&I | 00-104_B10 | CEILING LAYOUT- WAREHOUSE OFF+ SAMPLING LAB FR_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
79 |  | C&I | 00-104_B11 | CEILING LAYOUT- PRODUCTION OFFICE FR_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
80 |  | C&I | 00-104_C12 | CEILING LAYOUT- MAINTAINANCE OFFICE | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
81 |  | C&I | 00-104_C13 | CEILING LAYOUT- SECURITY OFFICE | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
82 |  | C&I | 00-104-B7 | CEILING LAYOUT- ADMIN FR | AutoCAD & PDF | R0 | 13/07/2019 | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
83 |  | C&I | 01-104_A2 | CEILING LAYOUT- QC LAB FL_ | AutoCAD & PDF | R0 | Not mentioned in Drawing | 2019-08-12 | R0-P-WIP | 2019-08-23 | 2019-08-23
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +shalendra@acmeinteriors.co.in This column is empty. Please make sure this coloumn is must to fill. _Assigned to Shalendra_ -Wilma Pereira

## Critical Issues
CRITICAL ISSUES AND ACTION TAKEN REPORT | [6 empty] | OPEN
SL. NO | DATE | RAISED BY | CRITICAL ISSUES | DEPENDENCIES | RESPONSE FROM CONCERNED TEAM | STATUS (OPEN/CLOSED) | CLOSED

## Supply Chain Tracker
SUPPLY CHAIN TRACKER - TO BE UPDATED BY PROCUREMENT
DETAILS AS PER BOQ & NON TENDERED ITEMS | [5 empty] | SAMPLE SUBMISSION & APPROVAL STATUS | [5 empty] | DETAILS REQUIRED FROM ALL VENDORS
Sr. No. | BOQ No | BRIEF DESCRIPTION | MAKE/ MODEL | QTY | UNIT | DATE OF SUBMISSION | LEAD TIME | DELIVERY REQUIRED AS PER PROJECT SCHEDULE | MAKE/MODEL APPROVED | ANY COST IMPACT DUE TO CHANGE IN MAKE ? | DATE OF APPROVAL
[12 empty] | PO No. | PO DATE | DATE OF DELIVERY AS PER PO | ACTUAL DATE OF DELIVERY | REMARKS
ONLY LONG LEAD ITEMS OF CIVIL & MEP WORKS TO BE MENTIONED HERE
C&I
1 | Int 10, 22 | Italian Marble Flooring |  | 142.14 | SQM |  | 3 Weeks |  | Oppo Grey | No |  | 134 | 18.10.19 | Readily Avialable |  | Readily Available
2 | Int 11 | Vitrified Tile Flooring | Jhonson | 363.38 | SQM |  | 3 Weeks |  |  |  |  | 156 | 25.10.19 | 18th Nov
3 | Int 13 | Polished Concrete |  | 1600.82 | SQM |  | 4 Weeks | [6 empty] | Cancelled
4 | Int 14 | Static Conductive VinylFlooring | Tarkett/Responsive/LG | 1827.21 | SQM |  | 10 Weeks |  | Tarkett |  | 27/08/19 | 135 | 18.10.19 | Readily Avialable |  | Readily Avialable, required at site by End of Nov
5 | Int 15 | Water proofing |  | 1827.21 | SQM |  | 2 Weeks | [6 empty] | 1st Nov
6 | Int 16 | Rubber Flooring | Tarkett/Responsive/LG | 43.66 | SQM |  | 4 Weeks | [8 empty] | Confirmation pending
7 | Int 18,19,21 | Vitrified Dado Tile - Wooden Finish | Nitco | 2165.72 | SQM |  | 4 Weeks |  |  |  |  | 123 | 11.10.19 | 1st Nov
9 | Int 20 | Brick clay Pattern |  | 75.85 | SQM |  | 4 Weeks |  |  |  |  | 101 | 05.10.19 | Delivered
12 | Int 23 | Coved vinyl skirting | Tarkett/Responsive/LG | 1405 | RMT |  | 4 Weeks |  |  |  |  | 135 | 18.10.19
13 | Int 25, 26. 27 | Granite Door / Windowjambs ( 3" + 4" ) |  | 215.18 | RMT |  | 4 Weeks | [8 empty] | Confirmation on Granite shade is pending on mail
16 | Int 28 | Counter in Corian top with storage below | LG/Staron | 48.85 | SMT |  | 5 Weeks | [8 empty] | Approval pending
17 | Int 29 | Counter in Granite top with storage below |  | 17.79 | SMT |  | 5 Weeks | [8 empty] | Get Black
18 | Int 31 | S.S Trolleys for Pantry |  | 12 | Nos |  | 5 Weeks | [8 empty] | Confirmation pending from BD
19 |  | Plain Gyp Board / Fireline Gyp Board / G.I Channels | Gyproc | As per BOQ | SMT |  | 2 Weeks |  |  |  |  | 154 | 25.10.19
20 |  | Ply & Laminates | Green Ply / Merino | As per BOQ | SMT |  | 2 Weeks
21 | Int C-11 | Aluminium Skirting 50mm high | Bottomline | 570.5 | RMT |  | 3 Weeks |  | Bottomline |  | 27/08/19 |  |  | Redily Availabla
22 | Int C-27 | Corrugated Sheet panelling |  | 72.45 | SMT |  | 3 Weeks |  |  |  |  | Cash Purchase |  |  |  | Sample for corragated is pending
23 | Int C-28 | Natural Indoor Green Wall |  | 60.48 | SMT |  | 4 Weeks | [8 empty] | Vendor is to visit the site
24 | Int C-29 | Aluminum corner guards | Bottomline | 125 | RMT |  | 2 Weeks | [6 empty] | Readily Available
25 | Int D-2.1 | Automatic Sliding Door :-1200 x 2400 | Otic/Kubic | 3 | Nos |  | 5 Weeks | [6 empty] | Cancelled
26 | Int D-2.2 | Toughened Glass Stile Door with Aluminum Door Frame | Otic/Kubic | 30 | Nos |  | 5 Weeks | [6 empty] | Readily Available
27 | Int D-2.3 | Vision Panel Solid flush Door with Aluminum Door Frame | Otic/Kubic | 36 | Nos |  | 5 Weeks | [6 empty] | Readily Available |  | Laminate shade should be approved by BD
28 | Int D-2.4 | Vision Panel Solid flush Door without door frame |  | 4 | Nos |  | 5 Weeks | [6 empty] | Readily Available
29 | Int D-2.5 | FIRE DOOR | Hormann | 3 | Nos |  | 5 Weeks |  |  |  |  | 147 | 22.10.19 | 30th Nov
30 | Int D-4 | Reception Table - 2800 x 750mm |  | 2 | Nos |  | 5 Weeks | [8 empty] | No details from BD
31 | Int D-5 | Mirror | SGG | 30 | SMT |  | 2 Weeks
33 |  | Gypsum Ceiling Material | Gyproc | As per BOQ | SMT |  | 2 Weeks |  |  |  |  | 154 | 25.10.19
34 | Int E-3 | Modular Grid Ceiling - 0.9NRC (600 X 600) | AMF/Ecofon | 136.32 | SMT |  | 5 Weeks |  | Ecofon |  | 27/08/19 | 159 | 30.10.19 | Readily Available |  | Only grid to be delivered
35 | Int E-5 | Metal Grid Ceiling | Armstrong | 2619.84 | SMT |  | 5 Weeks |  | Armstrong |  | 27/08/19 | 103 | 07.10.19
36 | Int E-6 | Wooden Baffle ceiling |  | 125.44 | SMT |  | 5 Weeks |  | Hunter Dogulas |  | 27/08/19 |  |  |  |  | Dhop drawing approval pending
37 | Int E-7 | AcousticBaffles Ceiling | Ecofon | 1161 | Nos |  | 8 Weeks |  | Ecofon |  | 27/08/19 |  |  |  |  | Material Avialable will be delivered by End of Nov
38 | Int E-8 | 1200 X 1200mm Acoustic hanging Panels |  | 57 | Nos |  | 5 Weeks |  | Ecofon |  | 27/08/19 |  |  |  |  | Material Avialable will be delivered by End of Nov
40 | Int E-13 | Hanging Pet Sheet |  | 106.03 | SMT |  | 8 Weeks |  | Ecofon |  | 27/08/19 |  |  |  |  | Clarity is pending from BD
41 | Int F-1 | Roller Blinds |  | 835.25 | SMT |  | 5 Weeks | [8 empty] | Clarity is pending from BD
42 | Int F-2 | Blackout Blinds same as above. |  | 50.05 | SMT |  | 5 Weeks | [8 empty] | Clarity is pending from BD
43 | Int F-3 | Electrical Motor for Blinds |  | 2 | Nos |  | 5 Weeks | [8 empty] | Clarity is pending from BD
44 | Int F-4 | Remote for blinds motors |  | 2 | Nos |  | 5 Weeks | [8 empty] | Clarity is pending from BD
45 | Int F-5 | Glass Marker Board | SGG | 196.04 | SMT |  | 4 Weeks |  | SGG Planilaque |  | 27/08/19 |  |  |  |  | Clarity is pending from BD
46 | Int F-6 | Carpet Profile. | Bottomline | 36.69 | RMT |  | 4 Weeks | [8 empty] | Selection pending
47 | Int F-7 | Acoustic Wall Paper |  | 656.1 | SMT |  | 5 Weeks | [8 empty] | Clarity is pending from BD, sample to be shared
49 | Int F-9 | FALSE FLOORING 300mm High | Unitile | 41.82 | SMT |  | 4 Weeks | [6 empty] | Redily abailable
51 | Int F-13 | SS Finish Duster stand - Size (300mm x 100mm x 100mm) |  | 21 | Nos |  | 5 Weeks | [8 empty] | Sample approval is pending
52 | Int F-15/16/17 | Artificial Plants |  | 231 | Nos |  | 4 Weeks | [8 empty] | Clarity is pending from BD
53 | Int F-18 | Entrance Mat |  | 130 | Nos |  | 2 Weeks | [6 empty] | Redily Available
54 | Int F-24 | Fire Stop | 3M/Hilti | 26 | Nos |  | 2 Weeks | [8 empty] | Techs Specs to be shared
55 | Int E - 1 to 8 | Sanitary Fixtures | Kohler/Jaquar | As per BOQ | Nos |  | 4 Weeks
56 | Int F - 1 to 12 | Kitchen Equipments | Kitchenmagic | As per BOQ | Nos |  | 8 Weeks | [8 empty] | Clearity pending from BD
57 | F-1 | Frosted film Basic |  | 155.71 | SMT |  | 4 Weeks | [8 empty] | Confirmation from BD is pending
58 | F-2 | Sun Contorl Film |  | 20 | SMT |  | 4 Weeks | [8 empty] | Confirmation from BD is pending
59 | F-3 | Graphics |  | 430.5 | SMT |  | 6 weeks | [8 empty] | Confirmation from BD is pending
60 | F-4 to 7 | Signages & Logo |  | As per BOQ | Nos |  | 6 weeks | [8 empty] | Confirmation from BD is pending
61 | Toilet - 3 | Waterproofing |  | 324.42 | SMT |  | 2 Weeks
62 | Toilet - 9.2 | Vitrified Tile Flooring | Nitco | 324.42 | SMT |  | 4 Weeks
63 | Toilet - 10 | Vitrified Tile Dado | Nitco | 1201.95 | SMT |  | 4 Weeks
64 | Toilet - 12 | Glass Urinal Partition |  | 18.828 | SMT |  | 3 Weeks
65 | Toilet - D | Loose Furniture |  | As per BOQ | SMT |  | 5 Weeks
66 | Toilet F-1 | Metal Grid Ceiling | Armstrong | 324.42 | SMT |  | 4 Weeks |  | Armstrong |  | 27/08/19
67 | Toilet - F | Sanitary Fixtures | Kohler/Jaquar | As per BOQ | Nos |  | 6 weeks
|  | Toilet Cubicle | Merino | [10 empty] | 30th Nov
| NT | Traps
MEP
HVAC
1 | HVAC BOQ-1.1 a | VRF Out Door Unit | Daikin | 12 | Nos | 2019-09-11 | 4-6 Weeks | 2019-10-26 | Daikin |  | 2019-09-17 |  |  |  |  | Order placement has not been done yet.
2 | HVAC BOQ-1.1 (i - iv) | VRF Indoor Unit | Daikin | 23 | Nos | 2019-09-11 | 4-6 Weeks | 2019-10-26 | Daikin |  | 2019-09-17
3 | HVAC BOQ-1.1 c | Treated Fresh Air Chilled Water AHU & Exhaust air handling unit | Zeco | 12 | Nos | 2019-09-11 | 8-9 Weeks | 2019-11-10 | Zeco |  | 2019-10-18
4 | HVAC BOQ-1.1 d | AHU with VRF ODU connectivity | Zeco | 6 | Nos | 2019-09-11 | 8-9 Weeks | 2019-11-10 | Zeco |  | 2019-10-18 | VRV-TN/158/ IFF -Tada 19-20 | 2019-10-23 | NA
5 | HVAC BOQ-1.1 (e - g) | VRF Controllers | Daikin | 1 | Lot | 2019-09-11 | 4-6 Weeks | 2019-11-10 | Daikin |  | 2019-09-17
6 | HVAC BOQ-5 | Chilled water Piping, Drain Pipe and Insulations | Jindal | 1 | Lot | 2019-09-11 | 3-4 Weeks | 2019-10-25 | Jindal |  | 2019-09-17 |  |  |  |  | will be closed on 21st Oct
7 | HVAC BOQ-6 | Exhaust and FA fans | Carryaire | 11 | Nos | 2019-09-11 | 4-5 Weeks | 2019-11-15 | Carryaire |  | 2019-09-23 |  | 19-10-19
8 | HVAC BOQ-7.1 | Rectangular Duct | Rolastar | 1 | Lot | 2019-09-11 | 1-2 Weeks | 2019-10-20 | COSMIC |  | 2019-09-20 | VRV-TN/161/ IFF -Tada 19-20 | 2019-10-29 | 2019-10-31
9 | HVAC BOQ-7.3 | Elliptical Duct | GP Spira | 1 | Lot | 2019-09-11 | 2-3 Weeks | 2019-10-20 | GP Spira |  | 2019-09-26 | VRV-TN/156/ IFF -Tada 19-20 | 2019-10-22 |  |  | will be closed on 18th Oct
10 | HVAC BOQ-7.6 - 7.17 | Grills and Diffusers | Cosmos | 1 | Lot | 2019-09-11 | 5-7 Weeks | 2019-11-10 | Cosmos |  | 2019-09-20 | VRV-TN/156/ IFF -Tada 19-20 | 18-10-19 |  |  | will be closed on 18th Oct
11 | HVAC BOQ-8 | DX Units | Daikin | 9 | Nos | 2019-09-11 | 2-3 Weeks | 2019-10-22 | Daikin |  | 2019-09-20 | VRV-TN/156/ IFF -Tada 19-20 | 17-10-19 | 28-10-19
12 | HVAC BOQ-9 | Air Washer Units | LUWA and LUFTEK | 2 | Nos | 2019-10-14 | 6-8 Weeks | 2019-11-10 | Luftek/ Luwa |  | Approval pending
13 | HVAC BOQ-10 | Thermal & Accoustic Insulation | Armaflex | 1 | Lot | 2019-09-11 | 2-3 Weeks | 2019-10-20 | Armaflex |  | 2019-09-17 | VRV-TN/159/ IFF -Tada 19-20 | 2019-10-21 | 28-10-19 |  | will be closed on 19th Oct
14 | HVAC BOQ-11.1 | Diffrential pressure transmitter & Sensor | Honeywell | 1 | Lot | 2019-09-11 | 4-5 Weeks | 2019-10-31 | Honeywell |  | 2019-09-17 |  |  |  |  | 21st Oct
15 | HVAC BOQ-11.3 | VAV | Cosmos | 66 | Nos | 2019-09-11 | 4-5 Weeks | 2019-10-31 | Cosmos |  | 2019-09-20 |  | 18-10-19 |  |  | will be closed on 18th Oct
16 | HVAC BOQ- 11.4 - 11.7 | Controls & Cables for VAV | Honeywell | 1 | Lot | 2019-09-11 | 4-5 Weeks | 2019-10-18 | Honeywell |  | 2019-09-17
17 | HVAC BOQ-8.3 | PLC for DX units | TBC |  |  | Pending Submission | 4 weeks | 2019-11-15 | TBC |  | Pending Submission
18 | HVAC BOQ-1c, 1D | VFD And starter panel for AHU | ABB |  |  | 2019-10-16 | 6 -7weeks | 2019-11-15 | TBC |  | pending Approval
19 | HVAC BOQ-11.4B | VAV touch screen | Honeywell |  |  | Further clarification required for submission.Parallely VRV is disuccing this with Honeywell on 17th Oct for a better understanding. | 6 weeks | 2019-11-15 | Honeywell |  | Pending Submission
20 | HVAC-BOQ-after 11.8 | VAV Logic controllers | TBC |  |  | Further clarification required for submission.Parallely VRV is disuccing this with Honeywell on 17th Oct for a better understanding. | 6 weeks | 2019-11-15 | TBC |  | Pending Submission
21 |  | Cable tray
22 |  | Drain pump | ASPEN
23 |  | Drain pipes | Supreme CPVC
24 |  | TFA | Daikin
25 |  | copper pipes | MEXFLOW
Electrical
1 | ELectrical BOQ-A1 | Panels | Powercon |  |  | GA approval pending from JACOBS | 5 weeks | 2019-10-15 | Powercon |  | 10th Oct 2019
2 | Electrical BOQ-C | cable trays powder coated | Nideax |  |  | 2019-08-22 | 4 weeks | 2019-10-18 | Nideax |  | 2019-08-26 | 3895 | 2019-09-24 | 2019-10-22
3 | Electrical BOQ-C | Raceways | Jindal |  |  | 2019-08-22 | 4 weeks | 2019-10-01 | Jindal |  | 2019-08-26 | 3882 | 2019-09-21 | Delivered
4 | Electrical BOQ-E | Lights | Ligthting technologies |  |  | 2019-09-09 | 5 weeks | 2019-10-30 | Lighting Technologies |  | 05th Oct 2019 | 3979 and 3980 | 2019-10-22 | 2019-11-23 |  | 15th Nov as per manufacturer
5 | Electrical BOQ -B | Conduits GI | BEC |  |  | 2019-08-22 | 2 Weeks | 2019-10-03 | BEC |  | 2019-08-26 | 3851 | 2019-09-14 | Delivered
6 | Electrical BOQ-B | cables & Wires | KEI |  |  | 2019-08-22 | 5 Weeks | 2019-10-24 | BEC |  | 2019-08-26 | 3938 | 2019-10-03 | Ready for delivery
7 | Electrical BOQ -B | LT cables | KEI |  |  | 2019-08-22 | 5 Weeks | 2019-10-24 | BEC |  | 2019-08-26 | 3938 | 2019-10-03 | Ready for delivery
8 | Electrical BOQ-A | DB | Siemens |  |  | 2019-08-22 | 2 Weeks | 2019-11-15 | Siemens |  | 2019-08-26 | 3919 | 2019-09-28 | Delivered
9 | Electrical BOQ-E | Lighting sensors | Philips |  |  | 2019-09-19 | 5 Weeks | 2019-11-15 | Lighting Technologies |  | 2019-10-05 | 3979 and 3980 | 2019-10-22 | 2019-11-23
10 | Electrical BOQ-A | MCB | Siemens |  |  | 2019-08-22 | 3 weeks | 2019-11-15 | Siemens |  | 2019-08-26 | 3919 | 2019-09-28 | Ready for delivery
11 | Electrical BOQ-H7 | Rubber mats | VoltMat |  |  | 2019-09-19 | 5 Weeks | 2019-11-15 | Pending Approval |  | Pending Approval
12 |  | Switches, sockets and Backboxes | Legrand | [5 empty] | Legrand Myrius |  | 2019-10-16 |  |  | 2019-10-31
PHE
1 | PHE-BOQ-A10 | Instantaneous water heater | Jaquar |  |  | 2019-10-05 | 3 weeks | 2019-10-31 | Jaquar |  | 2019-10-05
2 | PHE BOQ-B14,B16,17 | FRP manhole cover | Thermodrain |  |  | 2019-10-04 | 4 weeks | 2019-11-20 | Thermodrain |  | 2019-10-05
3 | PHE BOQ-B21 | Grease trap | NU Green |  |  | 2019-10-04 | 5 Weeks | 2019-11-22 | NU Green |  | 2019-10-05
4 | PHE BOQ A19 | Inline booster system | Grundfos |  |  | 2019-10-04 | 12 Weeks | 2019-11-22 | Grundfos |  | 2019-10-22
5 | PHE BOQ A16 | Butterfly valves | Zoloto |  |  | 2019-10-04 | 3 Weeks | 2019-11-22 | Zoloto |  | 2019-10-05
6 | PHE BOQ-A4 | Ball valves, NRV and Y strainer | Zoloto |  |  | 2019-10-04 | 3 Weeks | 2019-10-15 | Zoloto |  | 2019-10-05
7 | PHE BO-B9 | SS gratings | Chilly |  |  | 2019-10-04 | 3 Weeks | 2019-11-22 | Chilly |  | 2019-10-05
8 | PHE BOQ-B8 | Floor clean out | Chilly |  |  | 2019-10-04 | 3 Weeks | 2019-11-22 | Chilly |  | 2019-10-05
9 | PHE BOQ-B22 | SS gratings for Kitchen 600X300mm | TBC |  |  | Pending from Procurement | 4 weeks | 2019-10-31 | TBC |  | Pending
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +smit@acmeinteriors.co.in +suvin@acmeinteriors.co.in Please update this sheet immediately. _Assigned to Smit_ -Wilma Pereira
Note on P14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +sudhan.gunagi@acmeinteriors.co.in Update the date of delivery _Assigned to Sudhan Gunagi_ -Wilma Pereira Dear ma'am, I'm updating google sheet on daily basis for receiving materials but issue details will update late ( night or Sunday time i will update google sheet). henceforth will update daily basis for both transaction.. -Sudhan Gunagi
Note on I86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: fill this
Note on A133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +smit@acmeinteriors.co.in this is pendinga s the spec sheet shared does not mention a frame. _Assigned to Smit_ -sibin

## Weekly Progress Tracking
WEEKLY PROJECT PROGRESS TRACKING REPORT
WEEK No: | PLANNED ACTIVITIES FOR THE WEEK | DEPENDENT ACTIVITY | LOCATION | SPECIFY AREA | START DATE | END DATE | TARGETTED % OF PROGRESS | ACHIEVED % OF PROGRESS | REASON FOR ANY LAG
Week 1 | A2 ( QC Lab Flavors)
| Block Work | Gypsum Plaster | A2 ( QC Lab Flavors) | FL Block | 30.09.19 | 06.10.19 | 40% | 35%
| Floor raceway laying | PCC Screeding | A2 ( QC Lab Flavors) | FL Block | 30.09.19 | 06.10.19 | 40% | 0% | Due to no clearance at site
B7 ( Fragrance Admin)
| Block Work | Gypsum Plaster | B7 ( Fragrance Admin) | FR Block | 30.09.19 | 06.10.19 | 40% | 40%
| Floor Raceway Laying | PCC Screeding | B7 ( Fragrance Admin) | FR Block | 30.09.19 | 06.10.19 | 40% | 40%
| Plumbing piping | Waterproofing, Cinder filling, Tiling | B7 ( Fragrance Admin) | FR Block | 30.09.19 | 06.10.19 | 40% | 30% | Due to late clearance from Civil team
B8 ( Pia/ R&D Lab)
| Block Work | Gypsum Plaster | B8 ( Pia/ R&D Lab) | FR Block | 30.09.19 | 06.10.19 | 40% | 30% | Due to manpower issue
| Floor Raceway Laying | PCC Screeding | B8 ( Pia/ R&D Lab) | FR Block | 30.09.19 | 06.10.19 | 40% | 40%
| Plumbing piping | Waterproofing, Cinder filling, Tiling | B8 ( Pia/ R&D Lab) | FR Block | 30.09.19 | 06.10.19 | 15%
B9 ( Fragrance QC Lab)
| Block Work | Gypsum Plaster | B9 ( Fragrance QC Lab) | FR Block | 30.09.19 | 06.10.19 | 30% | 25% | Due to manpower issue
| Floor Raceway Laying | PCC Screeding | B9 ( Fragrance QC Lab) | FR Block | 30.09.19 | 06.10.19 | 30% | 30%
C13 ( Security OFF )
| Block Work | Gypsum Plaster, Plumbing works | C13 ( Security OFF ) | Security office | 30.09.19 | 06.10.19 | 30% | 25% | Due to manpower issue and No elcetricity for night shift work extension
WEEK 2
Week 2 | A2 ( QC Lab Flavors)
| Block Work | Gypsum Plaster | A2 ( QC Lab Flavors) | FL Block | 07.10.19 | 13.10.19 | 75% | 75%
| Floor raceway laying | PCC Screeding | A2 ( QC Lab Flavors) | FL Block | 07.10.19 | 13.10.19 | 25% | 95%
| HVAC Duct supporting works | Hvac Ducting installation | A2 ( QC Lab Flavors) | FL Block | 07.10.19 | 13.10.19 | 50% | 0% | Because of less manpower, MS grid
| Electrical Conduiting works | Electrical wiring and cabling works | A2 ( QC Lab Flavors) | FL Block | 07.10.19 | 13.10.19 | 50% | 0% | Because of less manpower, MS grid
| PCC Screeding works | Flooring works | A2 ( QC Lab Flavors) | FL Block | 07.10.19 | 13.10.19 | 30% | 0% | No clearancce and Vendor issue
| Gypsum Plaster works | Painting and other works | A2 ( QC Lab Flavors) | FL Block | 07.10.19 | 13.10.19 | 20% | 0% | Because of Block work, and delay in vendor finalisation
B7 ( Fragrance Admin)
| Block Work | Gypsum Plaster | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 75% | 75%
| Floor Raceway Laying | PCC Screeding | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 40% | 100%
| Plumbing piping drainage works | Waterproofing, Cinder filling, Tiling | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 65% | 80%
| HVAC Duct supporting works | Hvac Ducting installation | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 75% | 60%
| Electrical Conduiting works | Electrical wiring and cabling works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 40% | 10% | Because of manpower and Tools issue
| PCC Screeding works | Drywall partition works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 70% | 0% | Because of Vendor issue and site clearance
| Temporary Ply partition | Drywall partition works and other gypsum plaster works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 100% | 100%
| Gypsum Plaster works | Painting and other works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 15% | 0% | Because of Vendor finalisation issue and site clearance
B8 ( Pia/ R&D Lab)
| Block Work | Gypsum Plaster | B8 ( Pia/ R&D Lab) | FR Block | 07.10.19 | 13.10.19 | 75% | 60%
| Floor Raceway Laying | PCC Screeding | B8 ( Pia/ R&D Lab) | FR Block | 07.10.19 | 13.10.19 | 50% | 100%
| Plumbing piping drainage | Waterproofing, Cinder filling, Tiling | B8 ( Pia/ R&D Lab) | FR Block | 07.10.19 | 13.10.19 | 50% | 0% | No clearance at
| HVAC Duct supporting works | Hvac Ducting installation | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 75% | 75%
| Electrical Conduiting works | Electrical wiring and cabling works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 40% | 10% | Because of manpower and Tools issue
| PCC Screeding works | Drywall partition works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 35% | 0%
| Temporary Ply partition | Drywall partition works and other gypsum plaster works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 100% | 100%
| Gypsum Plaster works | Painting and other works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 15% | 0% | Because of Vendor finalisation issue and site clearance
B9 ( Fragrance QC Lab)
| Block Work | Gypsum Plaster | B9 ( Fragrance QC Lab) | FR Block | 07.10.19 | 13.10.19 | 75% | 75%
| Floor Raceway Laying | PCC Screeding | B9 ( Fragrance QC Lab) | FR Block | 07.10.19 | 13.10.19 | 40% | 100%
| HVAC Duct supporting works | Hvac Ducting installation | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 75% | 0%
| Electrical Conduiting works | Electrical wiring and cabling works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 50% | 10%
| PCC Screeding works | Drywall partition works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 40% | 0%
| Temporary Ply partition | Drywall partition works and other gypsum plaster works | B7 ( Fragrance Admin) | FR Block | 07.10.19 | 13.10.19 | 100% | 100%
C13 ( Security OFF )
| Block Work | Gypsum Plaster, Plumbing works | C13 ( Security OFF ) | Security office | 07.10.19 | 13.10.19 | 75% | 60%
WEEK 3
Week 3 | A2 ( QC Lab Flavors)
| Block Work | Gypsum Plaster | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 100% | 80% | due to less manpower
| Lintel casting for doors | Block work | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 100% | 0% | due to less manpower
| Floor raceway laying | PCC Screeding | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 100% | 100%
| Electrical Conduiting works | Electrical wiring and cabling works | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 50% | 0% | Due to no clearance at site level
| PCC Screeding works | Flooring works | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 50% | 0% | Due to no clearance at site level
| Gypsum Plaster works | Painting and other works | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 15% | 0% | Due to no clearance at site level
B7 ( Fragrance Admin)
| Block Work | Gypsum Plaster | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 90% | due to less manpower
| Lintel casting for doors | Block work | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 0% | due to less manpower and incompletion of block work
| Plumbing piping water supply system | Waterproofing, Cinder filling, Tiling | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 65% | 65%
| Plumbing piping drainage system | Waterproofing, Cinder filling, Tiling | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 90%
| HVAC Duct supporting works | Hvac Ducting installation | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 90% | Due to less manpower
| Electrical Conduiting works | Electrical wiring and cabling works | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 70% | 10% | Due to less manpower
| PCC Screeding works | Drywall Partition works | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 70% | 25% | Due to no availabiliy of concerete Pump
B8 ( Pia/ R&D Lab)
| Block Work | Gypsum Plaster | B8 ( Pia/ R&D Lab) | FR Block | 14.10.19 | 20.10.19 | 90% | 80% | Due to less manpower
| Lintel casting for doors | Block work | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 0% | Due to less manpower
| Plumbing piping drainge works | Waterproofing, Cinder filling, Tiling | B8 ( Pia/ R&D Lab) | FR Block | 14.10.19 | 20.10.19 | 70% | 0% | Due to no clearance at site level
| Plumbing piping water supply system | Waterproofing, Cinder filling, Tiling | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 60% | 0% | Due to no clearance at site level
| HVAC Duct supporting works | Hvac Ducting installation | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 85% | 90%
| Electrical Conduiting works | Electrical wiring and cabling works | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 50% | 90%
| PCC Screeding works | Drywall partition works | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 30% | 60%
| Gypsum Plaster works | Painting and other works | A2 ( QC Lab Flavors) | FL Block | 14.10.19 | 20.10.19 | 15% | 0% | Due to no clearance at site level
B9 ( Fragrance QC Lab)
| Block Work | Gypsum Plaster | B9 ( Fragrance QC Lab) | FR Block | 14.10.19 | 20.10.19 | 90% | 75% | Due to less manpower
| Lintel casting for doors | Block work | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 75% | Due to less manpower
| HVAC Duct supporting works | Hvac Ducting installation | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 100% | 90% | Due to less manpower
| Electrical Conduiting works | Electrical wiring and cabling works | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 70% | 10% | Due to less manpower
| PCC Screeding works | Drywall partition works | B7 ( Fragrance Admin) | FR Block | 14.10.19 | 20.10.19 | 30% | 60%
C13 ( Security OFF )
| Block Work | Gypsum Plaster, Plumbing works | C13 ( Security OFF ) | Security office | 14.10.19 | 20.10.19 | 100% | 75% | Due to less manpower
| Lintel casting for doors | Block work | C13 ( Security OFF ) | Security office | 14.10.19 | 20.10.19 | 100% | 0% | Due to less manpower
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +harshad.shrikhande@acmeinteriors.co.in As per your schedule break down the activities on weekly basis and update in this sheet. _Assigned to Harshad Shrikhande_ -Wilma Pereira +harshad.shrikhande@acmeinteriors.co.in +vasanth.v@acmeinteriors.co.in Why this weeks work schedule is not being updated? _Reassigned to Vasanth V_ -Wilma Pereira +sibin@acmeinteriors.co.in MEP work schedule is not reflecting in the current week schedule. Please check the same. _Reassigned to sibin_ -Wilma Pereira